## Sheet1
No. | Issue Name | Issue Details | Developer Status | Tester | Comments | APK Build Version
1 | Broken Product Images (Problem User) | When logged in as problem_user, all product images on the Inventory page fail to load and are replaced by a placeholder "Dog" image. This affects the user experience significantly. | Open | QA Team | This is a known issue specific to the problem_user role but should be fixed if this mimics a production failure state. | v1.0.0 (Web)
2 | Checkout Input Field Disabled | On the "Checkout: Information" page, the "Last Name" input field is unresponsive or disabled when using the problem_user account, preventing the user from completing the purchase. | Open | QA Team | Critical blocker for this user persona. User cannot proceed to Step 2. | v1.0.0 (Web)
3 | Performance Latency (Glitch User) | Login process takes more than 5 seconds when using the performance_glitch_user account. The system hangs without a loading spinner, confusing the user. | In Progress | QA Team | Latency is consistently reproducible. Recommendation: Add a loading spinner if backend delay is unavoidable. | v1.0.0 (Web)
4 | Missing Input Validation (Special Chars) | The "First Name" and "Last Name" fields in Checkout accept special characters (e.g., !@#$%) and numbers. No validation error is displayed. | Assigned | QA Team | Validation should restrict input to alphabets only to prevent bad data entry. | v1.0.0 (Web)
5 | Sorting Functionality Failure | When logged in as problem_user, selecting any option from the sort dropdown (e.g., "Price low to high") does not reorder the product list. The list remains in default state. | Open | QA Team | Functional defect. Sorting logic seems disconnected for this user session. | v1.0.0 (Web)
6 | UI Misalignment (Add to Cart) | For visual_user, the "Add to Cart" button on the "Sauce Labs Backpack" card is misaligned and overlaps with the product price text. | Open | QA Team | Cosmetic issue but affects visual consistency. Needs CSS fix on the product card container. | v1.0.0 (Web)
7 | Cart Badge Persistence Issue | (Edge Case) Sometimes, removing an item from the Cart page does not immediately update the cart badge counter in the header until the page is refreshed. | Cannot Reproduce | QA Team | Intermittent issue. Hard to reproduce consistently. | v1.0.0 (Web)

## Sheet2
# | Bug ID | Issue | Severity | Status | User Persona | Related TCs
1 | BUG-001 | Broken product images (Dog placeholder) | HIGH | OPEN | problem_user | TC_AUTH_003, TC_INV_015–TC_INV_025
2 | BUG-002 | Last Name field disabled in checkout | CRITICAL | OPEN | problem_user | TC_CHK_037-040
3 | BUG-003 | Login takes >5 seconds, no loading spinner | MEDIUM | IN PROGRESS | performance_glitch_user | TC_AUTH_004
4 | BUG-004 | Special characters accepted in name fields | MEDIUM | ASSIGNED | All users | TC_CHK_040
5 | BUG-005 | Sorting dropdown non-functional | MEDIUM | OPEN | problem_user | TC_INV_016–018
6 | BUG-006 | Button overlaps with price text (CSS) | LOW | OPEN | visual_user | TC_INV_019
7 | BUG-007 | Cart badge lag after item removal | LOW | CANNOT REPRODUCE | All users | TC_CRT_031, TC_CRT_034